## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | As a researcher, I want to enter product details, target audience, and research objectives. | MUST HAVE | No Dependency | Himanshu Kumar | 3- Completed
1 | 1 | US-002 | As a researcher, I want to generate five synthetic personas for the selected product. | MUST HAVE | US-001 | Himanshu Kumar | 3- Completed
2 | 2 | US-003 | As a researcher, I want all generated personas to answer survey questions. | MUST HAVE | US-002 | Himanshu Kumar | 3- Completed
2 | 2 | US-004 | As a researcher, I want to interview a selected persona while retaining conversation history. | MUST HAVE | US-002 | Himanshu Kumar | 3- Completed
2 | 2 | US-005 | As a researcher, I want to extract insights from survey responses. | MUST HAVE | US-003 | Himanshu Kumar | 3- Completed
3 | 3 | US-006 | As a researcher, I want to score persona preferences and show reasoning and a decision. | MUST HAVE | US-002 | Himanshu Kumar | 3- Completed
3 | 3 | US-007 | As a researcher, I want a dashboard showing themes, approximate sentiment, persona quotes, and scores. | MUST HAVE | US-003, US-005, US-006 | Himanshu Kumar | 3- Completed
3 | 3 | US-008 | As a researcher, I want to download a structured PDF research report. | MUST HAVE | US-003, US-005, US-006 | Himanshu Kumar | 3- Completed
3 | 3 | US-009 | As a reviewer, I want the complete application workflow tested before presentation. | MUST HAVE | US-001 to US-008 | Himanshu Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | 1 | Create product input form and research objective workflow | 2026-08-03 | 2026-08-05 | Himanshu Kumar | Design | 3- Completed | 4
US-002 | 2 | Implement persona generation agent and persona data model | 2026-08-06 | 2026-08-14 | Himanshu Kumar | Coding | 3- Completed | 10
US-003 | 3 | Implement survey mode and save persona responses | 2026-08-17 | 2026-08-26 | Himanshu Kumar | Coding | 3- Completed | 8
US-004 | 4 | Implement interview mode and conversation history | 2026-08-27 | 2026-09-04 | Himanshu Kumar | Coding | 3- Completed | 8
US-005 | 5 | Implement insight extraction agent | 2026-09-07 | 2026-09-14 | Himanshu Kumar | Coding | 3- Completed | 7
US-006 | 1900-01-05 | Implement product validation scores and decisions | 2026-09-15 | 2026-09-22 | Himanshu Kumar | Coding | 3- Completed | 7
US-007 | 1900-01-06 | Build dashboard for themes, sentiment, quotes, and scores | 2026-09-23 | 2026-10-02 | Himanshu Kumar | Coding | 3- Completed | 9
US-008 | 1900-01-07 | Generate structured PDF report with research results and scores | 2026-10-03 | 2026-10-09 | Himanshu Kumar | Coding | 3- Completed | 7
US-009 | 1900-01-08 | Perform end-to-end testing and final project review | 2026-10-10 | 2026-10-20 | Himanshu Kumar | Testing | 3- Completed | 8
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Aug 5 | Clarifying project requirements and expected workflow. | Reviewed project goals and divided the system into agents and modules.
Sprint 1 | Aug 12 | Persona outputs were not always consistent. | Adjusted persona prompts and checked generated profiles.
Sprint 2 | Aug 20 | Connecting survey results with insight extraction. | Tested the survey-to-insight workflow and corrected integration issues.
Sprint 2 | Sep 2 | Maintaining context in persona interviews. | Added conversation history to the interview workflow.
Sprint 3 | Sep 18 | Scoring results needed clear decisions and explanations. | Connected scores with reasoning and Yes/Maybe/No decisions.
Sprint 3 | Sep 29 | Dashboard sentiment and themes needed careful interpretation. | Displayed them as approximate keyword-based indicators.
Sprint 4 | Oct 8 | PDF report needed to include validation scores. | Updated the report layout to include research findings and score details.
Sprint 4 | Oct 18 | Final workflow verification before presentation. | Manually checked persona generation, survey, interview, insights, scoring, dashboard, and PDF.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-08-03 | 2026-08-14 | Himanshu Kumar | Plan the product workflow before coding. | Changing requirements without writing them down. | Keep the code modular. | Created a clear flow and separated the system into agents.
2 | 2 | 2026-08-17 | 2026-09-14 | Himanshu Kumar | Test survey and interview features with multiple personas. | Assuming model outputs are always consistent. | Keep persona context and conversation history. | Tested survey and interview flows and improved prompt handling.
3 | 3 | 2026-09-15 | 2026-10-02 | Himanshu Kumar | Check how dashboard metrics are derived. | Presenting heuristic sentiment as definitive. | Show scores and persona quotes with context. | Labeled dashboard sentiment and theme clusters as approximate.
4 | 4 | 2026-10-03 | 2026-10-20 | Himanshu Kumar | Run end-to-end checks before final delivery. | Leaving final report generation until the end. | Keep the report structured and include limitations. | Completed PDF report integration and manual end-to-end verification.